| Goal #1 Educate the public on health and social issues related to opioid treatment. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Objectives | Activities | Responsible Party | Due date | Completed date |
| Facilitate presentations in the community using the AZ Rx Drug Misuse & Abuse Toolkit and other modalities | - Prevention Team presented to 261 individuals over several presentations between 7/1/24 and 6/30/25. | Jacquelynn Villa-Baze | 7/1/24 | 6/30/25 |
| Facilitate presentations in the community on Mental Health First Aid and Youth Mental Health First Aid | - Prevention Team provided Mental Health First Aid training to 9 community members between 7/1/24 and 6/30/25. The training includes a section on opioid use. - Prevention Team provided Youth Mental Health First Aid training to 7 community members between 7/1/24 and 6/30/25. Training includes a section on opioid use. | Jacquelynn Villa-Baze | 7/1/24 | 6/30/25 |

| Goal #2 Promote opioid education and treatment statewide. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Objectives | Activities | Responsible Party | Due date | Completed date |
| Collaborate with other local community MAT clinics in order to facilitate access to care and coordination | - Hope Center Clinical Supervisor attends the Opioid Collaboration Meeting. | Liana Soto | Monthly | Ongoing |
| Collaborate with local MAT clinic to discuss SAMHSA and AHCCCS 2024 changes and how to implement sustainability within the OTP program. | - Hope Center Clinical Supervisor attended meeting with CODAC leadership to share resources in implementing changes | Liana Soto | 1/28/25 | 1/28/25 |
| Collaborate with community stakeholders to address public health issues related to opioid use | - Clinical Supervisor has been a member of the Arizona Opioid Treatment Coalition for 2 years | Liana Soto | Quarterly | Ongoing |
| Collaborate with community stakeholders on mortality factors related to opioid abuse and overdose. | - Hope Center Clinical Supervisor is on the Pima County Medical Examiners Review Board. The Board reviews county mortalities related to opiates and devises training and/or community action plans. | Liana Soto | Ongoing | Ongoing |
| Stay informed and inform state policy on opioid treatment via involvement in boards | - Clinical Supervisor has been a member of the Arizona Opioid Treatment Coalition for 2 years. | Liana Soto | Ongoing | Ongoing |
| Comments: |  |  |  |  |

| Goal #3 Maintain positive relationships with facility neighbors and community. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Objectives | Activities | Responsible Party | Due date | Completed date |
| Designate a Community Liaison to act as the primary contact for neighbors and community members | - Administrative Coordinator with 15+ years of experience designated as Community Liaison. | Angel Valencia | 11/15/25 | 11/7/25 |
| Community Liaison will meet with neighboring businesses monthly to provide education/information and address any concerns | - Community Liaison performs visits with neighboring businesses and no concerns reported. - Results of neighbor visits will be documented and kept on file in the administration office at Hope Center. Noted concerns will become part of the work plan. | Angel Valencia | Monthly | Ongoing |
| Establish a perimeter around the clinic for targeted patrols by on site security guard in order to minimize loitering, littering, and other disturbance to the neighborhood | - Clinical Supervisor established a perimeter to include nearby businesses and residential. Security guard patrols this area and redirects clients found loitering. | Liana Soto | Daily | Ongoing |
| Inform center clients on the importance of being good neighbors | - Center staff will distribute a handout for clients outlining the perimeter and explaining the importance of being neighborly while at the clinic. | Liana Soto | Ongoing | Ongoing |
| Comments: Note that the two closest, adjacent neighbors to Hope Center are closed for business during center dosing hours. |  |  |  |  |